## WBSNew
L1 | L2 | L3 | WBS No | WBSTitle | Standard Cost | Standard Delivery in Calendar Days | Effort/Hours
C |  |  |  | Components
C | BBS |  | C-BBS | Bandwidth Backhaul System | 4300 | 21
C | BBS | ANT | C-BBS-ANT | Antenna - Bandwidth Backhaul System | 4000 | 21
C | BBS | CBL | C-BBS-CBL | Cable Coax - Bandwidth Backhaul System | 200 | 10
C | BBS | CON | C-BBS-CON | Connectors - Bandwidth Backhaul System | 100 | 7
C | BCS |  | C-BCS | Bandwidth Control System | 5800 | 21
C | BCS | CBL | C-BCS-CBL | Cables - Bandwidth Control System | 300 | 10
C | BCS | CHW | C-BCS-CHW | Computer Hardware - Bandwidth Control System | 4000 | 21
C | BCS | CSW | C-BCS-CSW | Computer SW - Bandwidth Control System | 1500 | 14
C | BDS |  | C-BDS | Bandwidth Distrubution System | 6400 | 21
C | BDS | AMP | C-BDS-AMP | Amplifier - Bandwidth Distrubution System | 800 | 14
C | BDS | ANT | C-BDS-ANT | Antenna - Bandwidth Distrubution System | 600 | 14
C | BDS | APC | C-BDS-APC | Access Point Cabinet - Bandwidth Distrubution System | 2200 | 21
C | BDS | CBL | C-BDS-CBL | Cable - Bandwidth Distrubution System | 150 | 7
C | BDS | CON | C-BDS-CON | Connectors - Bandwidth Distrubution System | 100 | 7
C | BDS | LGP | C-BDS-LGP | Lightning Protectors - Bandwidth Distrubution System | 150 | 10
C | BDS | POE | C-BDS-POE | Power Over Ethernet - Bandwidth Distrubution System | 200 | 10
C | BDS | WAP | C-BDS-WAP | Wireless Access Point - Bandwidth Distrubution System | 2200 | 21
C | BSS |  | C-BSS | Bandwidth Supply system | 10800 | 30
C | BSS | CBL | C-BSS-CBL | Cable - Bandwidth Supply system | 300 | 10
C | BSS | EQB | C-BSS-EQB | Equipment Building - Bandwidth Supply System | 8000 | 30
C | BSS | RTR | C-BSS-RTR | Router - Bandwidth Supply system | 2500 | 21
C | CPE |  | C-CPE | Customer Premise Equipment | 223 | 14
C | CPE | ANT | C-CPE-ANT | Antenna - Customer Premise Equipment | 25 | 14
C | CPE | BRK | C-CPE-BRK | Brackets - Customer Premise Equipment | 15 | 7
C | CPE | CBL | C-CPE-CBL | Cable - Customer Premise Equipment | 8 | 7
C | CPE | CWD | C-CPE-CWD | Wireless Device - Customer Premise Equipment | 175 | 14
C | NSS |  | C-NSS | Network Server System | 5500 | 21
C | NSS | CHW | C-NSS-CHW | Computer Hardware - Network Server System | 4000 | 21
C | NSS | CSW | C-NSS-CSW | Computer Software - Network Server System | 1500 | 14
C | TWR |  | C-TWR | Tower System | 14700 | 30
C | TWR | FRM | C-TWR-FRM | Tower Frame - Tower System | 6000 | 30
C | TWR | BLD | C-TWR-BLD | Building - Tower System | 4000 | 30
C | TWR | BRK | C-TWR-BRK | Brackets - Tower System | 200 | 10
C | TWR | FDN | C-TWR-FDN | Foundaton - Tower System | 3000 | 21
C | TWR | FEN | C-TWR-FEN | Fence - Tower System | 1500 | 14
C | UCS |  | C-UCS | Unified Communication System | 12850 | 21
C | UCS | CBL | C-UCS-CBL | Cable - Unified Communication System | 200 | 10
C | UCS | CHW | C-UCS-CHW | Computer Hardware - Unified Communication System | 2500 | 21
C | UCS | CSW | C-UCS-CSW | Computer SW - Unified Communication System | 3000 | 14
C | UCS | PBX | C-UCS-PBX | Private Branch Exchange - Unified Communication System | 5000 | 21
C | UCS | RTR | C-UCS-RTR | Router - Unified Communication System | 1200 | 14
C | UCS | SIP | C-UCS-SIP | SIP Trunk - Unified Communication System | 800 | 7
C | UCS | SPH | C-UCS-SPH | Smart Phone - Unified Communication System | 150 | 7
C | BRK | ASY | C-BRK-ASY | Assembly - Brackets | 180 | 3 | 4
C | CAB | ASY | C-CAB-ASY | Assembly - Cabinet | 420 | 3 | 8
C | CBL | ASY | C-CBL-ASY | Assembly - Coax Cable | 240 | 2 | 5
E |  |  | E | Engineering
E | ENG |  | E-BBS | Engineering Bandwidth Backhaul System | 1200 | 3 | 24
E | ENG |  | E-BCS | Engineering - Bandwidth Control System | 1600 | 4 | 32
E | ENG |  | E-BDS | Engineering - Bandwidth Distrubution System | 1200 | 3 | 24
E | ENG |  | E-BSS | Engineering - Bandwidth Supply system | 800 | 2 | 16
E | ENG |  | E-CPE | Engineering - Customer Premise Equipment | 400 | 1 | 8
E | ENG |  | E-NSS | Engineering - Network Server System | 1200 | 3 | 24
E | ENG |  | E-TWR | Engineering - Tower System | 800 | 2 | 16
E | ENG |  | E-UCS | Engineering - Unified Communication System | 1200 | 3 | 24
E | ENG |  | E-SVT | Site visit 2 days | 1400 | 2 | 16
E | ENG |  | E-SST | Site study | 2000 | 5 | 40
E | ENG |  | E-SLD | Site layout drawing | 800 | 2 | 16
E | ENG |  | E-NDD | Network design and drawing | 1200 | 3 | 24
E | ENG |  | E-TMN | Technical Manual | 2000 | 5 | 40
I |  |  |  | Installation
I | INS |  | I-BBS | Install - Bandwidth Backhaul System | 400 | 1 | 8
I | INS |  | I-BCS | Install - Bandwidth Control System | 2000 | 3 | 24
I | INS |  | I-BDS | Install - Bandwidth Distrubution System | 800 | 2 | 16
I | INS |  | I-BSS | Install - Bandwidth Supply System | 2000 | 3 | 24
I | INS |  | I-CPE | Install - Customer Premise Equipment | 300 | 1 | 6
I | INS |  | I-NSS | Install - Network Server System | 2000 | 2 | 16
I | INS |  | I-TWR | Install - Tower System | 2000 | 1 | 8
I | INS |  | I-UCS | Install - Unified Communication System | 1000 | 2 | 16
S |  |  |  | Start-up
S | STP |  | S-BBS | Startup - Bandwidth Backhaul System | 400 | 1 | 8
S | STP |  | S-BCS | Startup - Bandwidth Control System | 800 | 2 | 16
S | STP |  | S-BDS | Startup - Bandwidth Distrubution System | 400 | 1 | 8
S | STP |  | S-BSS | Startup - Bandwidth Supply system | 400 | 1 | 8
S | STP |  | S-CPE | Startup - Customer Premise Equipment | 1200 | 3 | 24
S | STP |  | S-NSS | Startup - Network Server System | 800 | 2 | 16
S | STP |  | S-TWR | Startup - Tower System | 400 | 1 | 8
S | STP |  | S-UCS | Startup - Unified Communication System | 800 | 2 | 16
T |  |  |  | Toubleshooting
T | BCU |  |  | Bandwidth Control Unit
T | SPT |  | T-BCU | Support - Bandwidth Control Unit | 200 | 1 | 4
T | CSW |  |  | Computer Software
T | SPT |  | T-CSW | Support - Computer Software | 200 | 1 | 4
T | CWD |  |  | Customer Wireless Device
T | SPT |  | T-CWD | Support - Customer Wireless Device | 100 | 1 | 2
T | RTR |  |  | Router
T | SPT |  | T-RTR | Support - Router | 200 | 1 | 4
T | SPT |  |  | General Support
T | SPT |  | T-SPT | Support - General Support | 400 | 1 | 8
T | WAP |  |  | Wireless Access Point
T | SPT |  | T-WAP | Support - Wireless Access Point | 200 | 1 | 4

## Assumptions
WBS Estimate Assumptions (mock/ballpark figures)
Internal labor day rate: $400/day (8 hrs) = $50/hr.
Source: Sample_Cost.xls, 'Estimate' tab, note '400/day is our cost'.
Engineering site-task costs (Site visit, Site study, Site layout drawing,
Network design and drawing, Technical Manual) taken directly from
Sample_Cost.xls 'Estimate' tab, 'Our Cost Total' column, rows 6-10.
Other Engineering, Installation, Startup, and Troubleshooting line items are
estimated by analogy at the same $400/day rate, scaled to a reasonable
number of days per subsystem - not sourced from the sample file.
Purchasing Support rows represent internal procurement/admin labor
(0.5-1 day per item), based on Sample_Cost.xls 'Procurement time' line
(2 days / $800). Separate from the vendor purchase cost, tracked under C.
Components (C) Standard Cost = estimated vendor supply cost; Effort/Hours
is left blank for all C rows since it is external vendor work.
Costs for Tower POP, Backhaul, Wired Network, and Premise Equipment items
are approximated from Sample_Cost.xls 'Our Cost Total' column; items with
no equivalent in the sample are estimated by analogy.
Components (C) Standard Delivery = estimated vendor lead time in calendar
days: ~7-14 days for stock hardware, ~14-21 days for specialized
electronics, ~21-30 days for structural items.
Components parent/system rows (e.g. C-BDS) use =SUM() of child rows for
Standard Cost and =MAX() for Standard Delivery.
L1/L2/L3 numbering (Components only, for now): L1=C, L2=system or item
code, L3=sub-component or process code; WBS No = L1-L2[-L3]. The former
Assembly (A) section was folded into Components under this scheme:
e.g. Assembly - Brackets is now C-BRK-ASY (L2=BRK item, L3=ASY process).
All hardcoded cost/delivery/hours cells are mock estimates (blue font) for
planning purposes only and should be validated against real vendor quotes
and current labor rates before use in an actual customer quote.