## Cost Estimate
Rankin Inlet, Arviat & Chesterfield Inlet — NWI Last Mile Wireless System
Mock Cost Estimate by WBS — 3-Community / 50-Subscriber Solution
Prepared by: Northern Wireless Inc. (NWI) ¦ Reference: NWI-EST-RANKIN-2026 Rev 0 ¦ Basis: WBSWithEstimatesV1.xlsx + Scope of Supply Summary
WBS No | Item | Unit | Qty | Unit Price | Our Cost Total | Cust Cost Total | Profit | Std. Delivery (Cal. Days) | Effort (Hrs) | Notes / Source Mapping
Engineering & Admin
E-SVT | Site visit (2 days) | Each | 1 | 1400 |  |  |  | 2 | 16 | Site study & conceptual design — kickoff site visit
E-SST | Site study | Days | 1 | 2000 |  |  |  | 5 | 40 | Site study & conceptual design
E-SLD | Site layout drawing | Days | 1 | 800 |  |  |  | 2 | 16 | Layout drawing and BOM
E-NDD | Network design and drawing | Days | 1 | 1200 |  |  |  | 3 | 24 | Network design and configuration drawings
E-TMN | Technical/Training Manual | Days | 1 | 2000 |  |  |  | 5 | 40 | Training manual documentation
E-BDS | Engineering — Base Station subsystem | Days | 1 | 1200 |  |  |  | 3 | 24 | Coordination — base station (Bandwidth Distribution System) engineering
E-BCS | Engineering — Wired Network subsystem | Days | 1 | 1600 |  |  |  | 4 | 32 | Coordination — wired network / bandwidth control gateway engineering
E-CPE | Engineering — Premise Equipment subsystem | Days | 1 | 400 |  |  |  | 1 | 8 | Coordination — CPE configuration template for 50 units
PM-COORD* | Project Management & Coordination | Days | 1 | 1600 |  |  |  | 4 | 32 | *By analogy at WBS $400/day rate (no dedicated WBS row); oversees engineering-to-startup handoff
PROC* | Procurement / Purchasing Support | Days | 1 | 800 |  |  |  | 2 | 16 | *Matches Sample Cost Template 'Procurement time' line (2 days / $800)
Subtotal — Engineering & Admin
Base Station
C-BDS-APC | Access Point Cabinet | Each | 1 | 2200 |  |  |  | 21 |  | 1 – Access point & cabinet
C-BDS-WAP | Wireless Access Point / Radio Card | Each | 2 | 2200 |  |  |  | 21 |  | 2 – Radio Card (AP radio modules)
C-BDS-ANT | Omni Antenna | Each | 2 | 600 |  |  |  | 14 |  | 2 – Antennas/Amplifier (antenna side)
C-BDS-AMP | Bi-Directional Amplifier | Each | 2 | 800 |  |  |  | 14 |  | 2 – Antennas/Amplifier (amplifier side)
C-BDS-CBL | Cable Coax | Each | 2 | 150 |  |  |  | 7 |  | 2 – Cabling and connectors (cable)
C-BDS-CON | Connectors | Each | 2 | 100 |  |  |  | 7 |  | 2 – Cabling and connectors (connectors)
C-BDS-LGP | Lightning Protection | Each | 1 | 150 |  |  |  | 10 |  | Power outage protection and power conditioning
C-BDS-POE | Power Over Ethernet / Conditioning | Each | 1 | 200 |  |  |  | 10 |  | Power outage protection and power conditioning
C-BRK-ASY | Mast Mounting Bracket Assembly | Each | 1 | 180 |  |  |  | 3 | 4 | Exclusions: NWI supplies bracket to mount antennas to mast (no full tower in this scope)
I-BDS | Install — Base Station | Each | 1 | 800 |  |  |  | 2 | 16 | Installation of equipment (base station)
S-BDS | Startup — Base Station | Each | 1 | 400 |  |  |  | 1 | 8 | On-the-ground / installed on-site testing (base station)
Subtotal — Base Station
Wired Network
C-BCS-CHW | Bandwidth Control Gateway — Hardware | Each | 1 | 4000 |  |  |  | 21 |  | Bandwidth control gateway
C-BCS-CSW | Bandwidth Control Gateway — Software | Each | 1 | 1500 |  |  |  | 14 |  | Bandwidth control gateway
C-BCS-CBL | Cable — Wired Network | Each | 1 | 300 |  |  |  | 10 |  | Wired network cabling
C-BSS-RTR | Router / Main Hub-Switch | Each | 1 | 2500 |  |  |  | 21 |  | Main Hub/switch
C-BCS-LGP* | Power Outage Protection & Conditioning | Each | 1 | 150 |  |  |  | 10 |  | *Wired network side; cost by analogy to C-BDS-LGP (no dedicated WBS row)
I-BCS | Install — Wired Network | Each | 1 | 2000 |  |  |  | 3 | 24 | Installation of equipment / configuration (wired network)
S-BCS | Startup — Wired Network | Each | 1 | 800 |  |  |  | 2 | 16 | On-the-ground / installed on-site testing (wired network)
Subtotal — Wired Network
Premise Equipment (Qty 50 Subscribers)
C-CPE-CWD | Modem/Radio (Wireless Device) | Each | 50 | 175 |  |  |  | 14 |  | 50 – Modem/Radio
C-CPE-ANT | Patch Antenna | Each | 50 | 25 |  |  |  | 14 |  | 50 – Patch Antenna
C-CPE-CBL | RF Cable with Connectors | Each | 50 | 8 |  |  |  | 7 |  | 50 – RF Cable with Connectors
C-CPE-BRK | Mounting Bracket | Each | 50 | 15 |  |  |  | 7 |  | Premise antenna mounting hardware
CPE-ETH* | Ethernet Cable & RJ45 Connectors | Each | 50 | 6 |  |  |  | 7 |  | *50 – Ethernet cable and RJ45 connectors; estimated by analogy (no dedicated WBS row)
I-CPE | Install — Premise Equipment | Each | 50 | 300 |  |  |  | 10 | 300 | Installation of equipment (premise); duration is crew-adjusted (2-person crew, ~5 installs/day) — NOT a simple x50 of the WBS per-unit day figure; effort hours (300 = 6 hrs x 50) do scale linearly
S-CPE | Startup — Premise Equipment (batch commissioning) | Each | 1 | 1200 |  |  |  | 3 | 24 | Installed on-site testing across all 50 premises (single batch commissioning task)
Subtotal — Premise Equipment
Installation & Commissioning — Supporting Items
SFTY-EQP* | Safety Climbing Equipment (rental/consumables) | Each | 1 | 250 |  |  |  | 2 |  | *Safety climbing equipment; estimated by analogy (no dedicated WBS row)
TOOLS-INS* | Installation Tools & Consumables | Each | 1 | 150 |  |  |  | 2 |  | *Tools for installation; estimated by analogy (no dedicated WBS row)
Subtotal — Installation & Commissioning (Supporting Items)
Note: per-subsystem install/startup ('installation of equipment', 'on-the-ground / installed on-site testing') costs are itemized within Base Station, Wired Network and Premise Equipment above.
Training
TRN-OJT | On-Site Training (customer personnel, 4-hr course) | Each | 1 | 200 |  |  |  | 1 | 4 | One-time local training course, 4 hours (Scope of Supply — Support Details). Training manual costed under Engineering (E-TMN)
Subtotal — Training
Support (2-Month Included Period)
T-WAP | Support — Wireless Access Point | Each | 1 | 200 |  |  |  | 1 | 4 | 24/7 technical support
T-BCU | Support — Bandwidth Control Unit | Each | 1 | 200 |  |  |  | 1 | 4 | 24/7 technical support
T-CSW | Support — Computer Software | Each | 1 | 200 |  |  |  | 1 | 4 | 24/7 technical support
T-RTR | Support — Router | Each | 1 | 200 |  |  |  | 1 | 4 | 24/7 technical support
T-CWD | Support — Customer Wireless Device (fleet) | Each | 1 | 100 |  |  |  | 1 | 2 | 24/7 technical support
T-SPT | Support — General (24/7 coordination + telephone support) | Each | 1 | 400 |  |  |  | 1 | 8 | Two months telephone support and remote administration included
Subtotal — Support (2-Month Included Period)
TOTAL — SUPPLY, INSTALL & COMMISSION
Assumptions & Methodology
• Source data: costs, unit prices and standard delivery spans are drawn from WBSWithEstimatesV1.xlsx (internal $400/day = $50/hr labor rate); quantities are drawn from ScopeOfSupplySummary-nwi-last-mile-system.md.
• Lines marked with * have no directly corresponding WBS row and are estimated by analogy to the nearest comparable WBS item, consistent with the source workbook's own Assumptions tab methodology.
• Component (hardware/software) 'Std. Delivery' is vendor lead time for the order as a whole and is NOT multiplied by quantity (bulk ordering 2 or 50 units does not take proportionally longer).
• Installation labor (I-CPE) hours DO scale with quantity (6 hrs/unit x 50 = 300 hrs total labor), but the calendar-day duration is crew-adjusted (assumes a 2-person install crew averaging ~5 premises/day) rather than a literal x50 of the single-unit WBS day figure.
• Startup/commissioning (S-*) rows represent a single batch verification task per subsystem, not a per-unit cost, and are held at Qty 1.
• Cust Cost Total = Our Cost Total x 1.30 (30% standard NWI markup); Profit = Cust Cost Total - Our Cost Total. Adjust the markup assumption in column H formulas as needed for a firm quote.
• Excludes: emergency backup power, firewalls, ISP services, spares, full tower/mast structure (bracket-mount only), NIC, and client VPN/encryption configuration — per Scope of Supply Summary Exclusions.
• Figures are mock/ballpark planning estimates only and should be validated against current vendor quotes and labor rates before use in a firm customer quote.